## How To Read
PARTNER JOURNEY DECISION MATRIX
Purpose | Every step from signature to steady state, interrogated: why it exists, who owns it, what each side does, what breaks without it, how it scales, and the mechanism that runs it.
The extra question added | Signal recorded. Every step must emit a data point into the dashboard. A step that emits nothing is invisible to the machine, and invisible steps cannot be improved, escalated or defended. If a step has no signal, either give it one or question the step.
Owner codes | PEM = Partner Enablement Manager (this role) ¦ PDM = Partner Development Manager ¦ FAE = Field Applications Engineer ¦ PTR = the partner ¦ BI = Business Intelligence (Fearghal's world)
Scalability codes | RAILS = automated / self-serve / group-based, runs on every partner at near-zero marginal cost ¦ OVERLAY = human 1:1, earned via qualification or pulled by signal ¦ HYBRID = rails by default, overlay when triggered
Reading rule | The two columns to argue with are 'What breaks without it' and 'Signal recorded'. If a step survives both questions, it stays. If not, it is ceremony.
Status | Working draft, 17 July 2026. Assumption-labelled. Track variations column covers software-partner and strategic-lane differences.

## Partner Journey
# | Phase / timing | Step | Why it matters | What breaks without it | Owner | Our agreed actions | Their agreed actions | Scalable how | Mechanism / instrument | Signal recorded | Track variations
PHASE 0 — RECRUIT AND QUALIFY (before day 0)
1 | Pre-signature | Identify and qualify the partner | Recruit for pipeline, not just capability. The census of existing Alliances relationships and Shane's community is the warm pool. | Cold-recruited partners with no live customer conversation become the dormant 40-60%. Recruitment quality is the single biggest lever on every downstream number. | PDM | Run the census of existing partner-adjacent activity. Score candidates: capability, live conversation named, evolution potential. | Disclose real pipeline honestly. Name an executive sponsor. | OVERLAY | Partner selection scorecard (entry criteria include a named live opportunity) | Candidate scored and source logged (census / community / inbound) | Strategic-bet lane candidates flagged here, Ryan sign-off required.
2 | Pre-signature | Qualification questionnaire | Their top 3 customer conversations where ADI could fit. Seeds opportunity #1 and sets the support level they get. | Kickoff becomes generic. No opportunity to anchor week one on. Support gets spent on partners who cannot use it. | PEM | Issue, chase, review. Decide rails vs overlay from the answers. | Complete it honestly before kickoff. Name people per role (engineer / seller / exec). | RAILS | Standard form in the PRM, auto-routed | Questionnaire completed Y/N + named-opportunity count | Software partners name a target integration instead of customer deals.
3 | Day -5 to 0 | Legal, portal and deal-reg provisioning | All admin dies before day one so partner-facing time is never spent on paperwork. | Week one becomes form-filling. Momentum gone before it exists. First impression: bureaucracy. | PEM | Agreement executed, portal credentials issued, deal-reg access live, welcome pack sent. | Sign, nominate users, log in once before kickoff. | RAILS | PRM automated provisioning + checklist | Provisioning complete date (SLA clock starts) | Same for all tracks.
PHASE 1 — WEEK ONE (day 1-7): the deal is the onboarding
4 | Day 1 | Kickoff | Jointly pick opportunity #1 from the questionnaire. Partner leaves with a named target, a named ADI contact and a date. | No anchor deal means training with no purpose, and the sign-up-then-silent pattern starts immediately. | PEM | Run it. Confirm roles both sides. Set the 90-day map and the day-7/30 dates. | Right people in the room: seller + engineer minimum. Commit to opportunity #1. | HYBRID | Group kickoff cohorts monthly (rails) / 1:1 for qualified partners (overlay) | Kickoff held date; opportunity #1 named Y/N | Strategic lane: kickoff sets a bespoke milestone map instead of the 30-day clock.
5 | Day 1 | Registration mechanics taught live | Partner drives the deal-reg screen at kickoff. Real opportunity if it genuinely exists, practice entry if not. Capability proven day one. | Self-service later is where week one dies. Untaught registration = empty portal = dead programme. | PEM | Screen-share walkthrough, partner's hands on the keyboard. | Their seller performs the registration personally. | RAILS | PRM deal-reg module + recorded walkthrough for cohorts | First portal registration event (real or practice, flagged which) | Software partners: sandbox access provisioned live instead.
6 | Day 4-5 | Working session on the live deal | FAE + their engineer on technical fit; PDM + their seller on the commercial angle. The deal is the classroom. | Opportunity #1 stalls untouched. Partner concludes the programme is a portal and a PDF. | PDM | FAE hours allocated from the pre-agreed cohort budget. Session booked by day 3. | Engineer and seller attend prepared, customer context shared. | OVERLAY | Pre-negotiated FAE allocation per cohort (the named dependency, agreed BEFORE launch) | Session held date (ADI-side SLA: booked by day 10 or internal escalation) | Software partners: FAE session = integration architecture review.
7 | Day 2-7 | Role-based training assigned | Framed as 'what you need for this deal', never a curriculum. Engineer, seller and exec get different paths. | Generic training gets ignored. Completion without relevance is the vanity-metric trap. | PEM | Assign paths from the content audit (reuse Product Enablement assets first). | Named people start their paths. | RAILS | LMS auto-assignment by role | Path started % within 7 days | Content flavoured by vertical later; structure identical.
8 | Day 7 | Checkpoint (30 min) | Registered? Session held? Blockers? First data point on the dashboard. | First fortnight drifts silently. Problems surface at day 30 when they are already expensive. | PEM | Run it, log it, fire any escalations. | Show up, be honest about blockers. | HYBRID | Standing 30-min slot / async check for rails cohort | Checkpoint held + blocker log entry | Same all tracks.
PHASE 2 — DAY 7-30: reality
9 | Target day 14 | First QUALIFIED registration | Named customer, named application, rough timeline. The test: would an ADI seller take it seriously? | Junk pipeline corrupts the dashboard AND manufactures the partner-vs-seller collision the sceptics predict. One hollow claim can cost the field's trust. | PTR | PEM reviews against the quality bar within 48h. PDM coaches if it fails review. | Register only real opportunities. Accept the quality bar. | RAILS | Quality bar checklist inside the deal-reg form | Time-to-first-qualified-registration (THE north-star metric, by cohort) | Software partners: activation = working proof (integration demonstrably running), not a registration.
10 | Day 7-30 | PAS live + early-warning triggers armed | Weighted activation score starts accruing. Triggers: no login 10 days, no content by 14, no registration by 21, checkpoint missed. | Disengagement gets noticed at day 60 when it is too late. The machine cannot manage what it cannot see. | PEM | Monitor dashboard. Diagnose fired triggers: partner-side, ADI-side, or fit. Route accordingly. | None. This is invisible machinery. | RAILS | PAS in the Dynamics-connected dashboard; automated trigger rules | PAS value + trigger events with owner and action taken | Strategic lane sits in a separate cohort; triggers set to its bespoke map.
11 | Day 30 | ACTIVATION GATE | First qualified registration exists, or the escalation ladder fires: PEM diagnoses, PDM re-engages commercially, ADI-side blockers fixed by PEM. | The 40-60% dormancy pattern. Zombies enter the denominator and the programme looks like it is failing even where it works. | PEM | Gate review. Fire the ladder if missed. Log cause honestly (recruitment error vs our friction vs fit). | Deliver the registration, or the honest reason why not. | RAILS | Gate rule in the dashboard + escalation ladder | Activation Y/N + days-to-activation + miss-cause code | Health check, not a stick: a genuine slower build triggers a conversation, or a move to the strategic lane.
PHASE 3 — DAY 30-60: prove the motion
12 | Day 30-60 | First joint customer meeting | Partner fronts it, ADI supports. The co-sell motion happens for real. | Programme stays theoretical. Partner never crosses from trained to selling. | PDM | Attend in support role. Debrief after. Coach the gap. | Book it, front it, run their own deck (brand-approved). | OVERLAY | Joint-meeting milestone in PAS | Meeting held date + debrief note | Software partners: equivalent = joint technical demo to a prospect.
13 | Day 30-60 | Opportunities 2 and 3 registered | One deal is luck. Three is a motion. | A single-deal partner is a project, not a partnership. No basis for tier progression. | PTR | PDM pipeline-coaches. PEM tracks velocity. | Source and register from their own book. | RAILS | Deal-reg + PAS weighting | Registration count + velocity | Software: additional proof points / second integration scope.
14 | Day 30-60 | Certification ~50% | Competence building in parallel. Gates tier benefits at day 90, never selling rights. | Partner sells without depth: quality risk downstream, FAE dependency never reduces. | PTR | PEM monitors completion, chases via the partner's exec sponsor if stalled. | Named people complete their paths. | RAILS | LMS tracking | Completion % by role | Engineer track heavier for software partners; seller track for solution partners.
PHASE 4 — DAY 60-90: independence
15 | Day 60-90 | Independent customer conversation | Partner runs a customer conversation with no ADI in the room. The point of enablement is our absence. | Permanent dependence: every partner deal consumes ADI headcount forever, which kills the scaling economics. | PTR | PDM available on-call only. Debrief after. | Run it alone, report back honestly. | RAILS | Self-reported + PDM verification | Independent meeting logged | Same principle all tracks.
16 | Day 60-90 | Opportunity #1 advances or dies honestly | Moves a funnel stage toward design-in, or is disqualified cleanly. A fast no is a healthy signal. | Polite fiction accumulates. Pipeline reviews become theatre. Fearghal's numbers rot. | PDM | Stage review with the partner. Kill or advance, never park. | Honest stage assessment. | RAILS | Funnel stage field in Dynamics | Stage change event (or DQ + reason) | Software: proof advances toward badge-worthy / production-ready.
17 | Day 90 | DAY-90 REVIEW: graduate / extend / re-tier | Every partner exits onboarding with an explicit status and a decision. No zombies. | The active cohort fills with dead weight. Metrics corrupt. Support gets spent where it returns nothing. | PEM | Prepare the evidence pack (PAS history, pipeline, cert). Recommend. Ryan decides contested cases. | Attend the review. Commit to the outcome. | RAILS | Day-90 review template + decision log | Exit status (graduate / extend+fix / re-tier) — cohort-level graduation rate | Extension always carries a NAMED fix and one more 30-day clock.
PHASE 5 — BEYOND 90: steady state and evolution
18 | Quarterly | QBR cadence | Performance, pipeline, plan. The relationship rhythm after the machine hands over. | Partners drift post-graduation. Year-two attrition arrives invisibly. | PDM | Run QBRs for managed tier; PEM supplies the data pack automatically. | Show up with their numbers and their asks. | HYBRID | Auto-generated QBR data pack from the dashboard | QBR held + actions logged | Rails tier gets an automated quarterly scorecard instead.
19 | Ongoing | Tier progression and track switching | Partners climb as certification and performance accrue. A hardware entrant switching on the commercial track IS the evolution engine. | Static partners. The programme never manufactures solution partners out of hardware ones, which was the growth thesis. | PEM | Review tier eligibility quarterly. Propose track additions when signals justify. | Invest in the next track when ready. | RAILS | Tier rules + PAS history | Tier changes + tracks-active per partner | The evolution arrow on the segmentation slide, operationalised.
20 | Monthly | Friction pulse and re-weighting loop | Three questions to every active partner monthly; PAS weights re-examined at month 6 against design-in outcomes. | The machine ossifies. V1 judgment hardens into dogma. The China lesson, unlearned. | PEM | Run the pulse, publish one process change per month, re-weight at month 6 with BI. | Answer three questions honestly. | RAILS | Pulse survey + cohort regression at month 6 | Friction log + weight-change record | The mechanism that makes every other row improve over time.